## Slide 1
MAKENA ENTERTAINMENT
PUNTA CANA GROUP TRIP 2026
Dominican Republic • November 2026
TRIP MANAGER'S PLAYBOOK
Your complete delegation & operations guide from the moment guests land to the moment they fly home.
🌴
One Life. Good Vibe. Party Hard.

## Slide 2
YOUR ROLE ON THIS TRIP
MANAGER · DELEGATOR · VISIONARY
You are not lifting boxes. You are not driving vans. You are not setting up tables. You show up, you oversee, you make decisions, and you make people feel like royalty.
👑
VISION
You set the standard. Every detail of this trip reflects your brand. Your team executes — you approve.
📋
DELEGATION
Every activity, every logistics task, every creative element is owned by a specific person or vendor. You assign, they deliver.
🎯
ACCOUNTABILITY
You hold daily check-ins with your delegate team. Nothing surprises you because you built the system in advance.

## Slide 3
BUILD YOUR DELEGATE TEAM
Assign these roles before the trip. Each person owns their lane.
🚐
Ground Coordinator (Punta Cana Local)
Your eyes & ears on the ground. Handles all local vendor relationships, on-site problem solving, and day-of logistics. Must speak English & Spanish.
✈️
Airport & Transport Lead
Manages all arrivals & departures. Coordinates driver team, MAKENA signs, vehicle schedules, and delayed flight protocol.
🏨
Hotel Liaison
Owns the hotel relationship. Pre-keys rooms, manages upgrades, handles guest issues, distributes welcome gift bags.
⛵
Activities Coordinator
Books and manages all excursions: catamaran, island trip, adventure day. Confirms headcounts, waivers, safety briefs.
🎉
Events & Nightlife Lead
Owns all party logistics: venue, DJ, decor, dress code comms, entry wristbands, photographer booking.
📸
Content Creator / Photographer
Captures everything. Photos, reels, BTS content. Delivers highlight reel by Day 5 farewell breakfast. Post-trip social content.
💬
Guest Services Lead
Manages guest WhatsApp group. First point of contact for questions, complaints, and special requests. Distributes all pre-trip info.
🛍️
Merch & Gifting Lead
Sources, designs, and fulfills all Makena branded items: gift bags, wristbands, hats, beach towels, and farewell gifts.

## Slide 4
PRE-TRIP MASTER CHECKLIST
Everything that must be locked in BEFORE a single guest lands.
CONTRACTS & BOOKINGS
Transportation company — airport fleet, MAKENA signs
Hotel block contract — room categories, rates, upgrades
Catamaran company — capacity, open bar, DJ, menu
Island day trip operator — speedboat, beach lunch
Adventure day vendor — dune buggies / ATVs / zip-line
Private dinner venue — menu, service, decor
Night party venue — DJ, sound, lighting, capacity
Professional photographer + videographer
BRANDING & GIFTING
Design & order Makena welcome gift bags (see Slide 6)
Branded wristbands (color-coded by event/day)
Makena bucket hats for island day trip
Custom matching jerseys for adventure day
Branded beach towels for resort days
Farewell keepsake gift (keychain / photo print)
MAKENA airport pickup signs (laminated, professional)
All White party entry arch / step-and-repeat backdrop
GUEST COMMUNICATIONS
Send full trip itinerary PDF to all guests (2 weeks before)
Create group WhatsApp with all guests
Collect all flight details & arrival times
Send All White dress code reminder (1 week + 1 day before)
Share packing list & weather advisory
Send hotel address, check-in time, room info
Build emergency contact sheet (local hospital, embassy)
Share adventure day waiver forms in advance
MONEY & ADMIN
Confirm all vendor deposits paid
Set up trip petty cash / on-the-ground fund
Arrange group travel insurance for all guests
Create a vendor contact sheet for each delegate
Build daily budget tracker
Confirm all Makena branded items have arrived
Create delegate briefing doc — each role's daily tasks
Schedule pre-trip team call (1 week before departure)

## Slide 5
✈️ AIRPORT ARRIVALS & TRANSPORTATION
Delegate: Airport & Transport Lead | First impression of the whole trip — make it count.
📋 ACTION ITEMS
Find & contract a reputable Punta Cana transportation company (vans/SUVs)
Collect every guest's flight number, airline & arrival time
Create 3–4 designated pickup windows (e.g. 10AM, 2PM, 6PM, 10PM)
Design laminated MAKENA branded pickup signs — bold, clean, on-brand
Brief every driver: dress code (black attire), behaviour, no phone use
Set up a driver group chat — Airport Lead manages this in real time
Create delayed-flight protocol: driver waits up to 90 min, then re-deploys
Map out route from Punta Cana Int'l Airport (PUJ) to resort
Arrange backup vehicle in case of no-shows or large group arrivals
Confirm vehicle capacity vs. max guests per window
✨ CREATIVE IDEAS (OUTSIDE THE BOX)
🎵 Makena Playlist in Every Vehicle
The moment guests get in the van, the Makena playlist is already playing. First vibe check — passed.
🥤 In-Van Welcome Pack on the Seat
Each seat has a small branded paper bag: cold water, Makena branded snack, a handwritten welcome card from Baldwin, and a wristband for the welcome mixer.
📸 Airport Sign Photo Moment
Design the MAKENA sign as a photo-worthy prop. Guests will post it. Free organic marketing for the brand.
💬 WhatsApp 'You've Landed' Ping
Guest Services Lead sends a personal WhatsApp to each guest the moment they confirm pickup: 'Welcome to DR! Your driver [Name] is waiting at door X.'
🚐 Branded Vehicle Wrap (Premium Option)
If budget allows, wrap at least one vehicle in Makena branding. It's a moving billboard at PUJ and on the road.
🎁 Surprise Upgrade Announcement
For VIP guests or upsells — driver discreetly hands them a card in the van: 'You've been upgraded to an ocean-view room. Welcome.'

## Slide 6
🏨 HOTEL CHECK-IN & WELCOME EXPERIENCE
Delegate: Hotel Liaison | The first hour at the resort sets the tone for everything that follows.
📋 ACTION ITEMS
Negotiate group block rate — confirm room categories (standard, deluxe, suite)
Pre-assign every guest to their room before they land — no waiting at front desk
Pre-key all rooms — envelopes with guest name + room number ready at check-in desk
Arrange early check-in for first arrival window guests (or holding lounge if unavailable)
Book Baldwin's suite as Trip HQ — spacious, central for team meetings
Confirm hotel has a welcome area for group arrival (lobby, terrace, or pool bar)
Arrange birthday / anniversary room decorations for any guest with a milestone
Brief hotel concierge on the full week's schedule so they can support guests
Confirm resort wristbands or room key system — integrate with Makena wristbands
Walk the hotel 24hr before first arrival — fix any issues before guests see them
🎁 MAKENA WELCOME GIFT BAG
Sitting in every room when guests arrive. Unboxing is the moment.
Makena Branded Tote Bag
The bag itself is the gift bag — reusable, branded, premium feel.
Custom Itinerary Card
A beautifully designed card with the week's schedule — nights, excursions, dress codes.
Handwritten Welcome Letter
Personal note from Baldwin. Short, warm, sets the tone. This will be photographed.
Makena Beach Towel
Oversized, thick, embroidered Makena logo. For the pool and the 'gram.
Branded Event Wristbands
Color-coded by event — guests wear to gain entry to each Makena event.
Sunscreen SPF 50 (Branded Label)
Custom Makena label on the bottle. Useful AND on-brand.
Mini First Aid Kit
Travel-size kit. Guests will appreciate the thoughtfulness.
Local Snack Box
Curated selection of DR snacks + a mini bottle of Mamajuana local liqueur.
Surprise QR Code Card
Links to a private Spotify playlist 'Makena Punta Cana 2026' — curated by Baldwin.

## Slide 7
DAY 1
ARRIVAL & WELCOME MIXER
Delegate: Hotel Liaison + Events Lead | Vibe: Casual, warm, get-to-know-you energy | Time: Sunset (6PM – 9PM)
📋 ACTION ITEMS
Reserve pool terrace or beach area exclusively for the group at sunset
Contract a mixologist or bartender — signature welcome cocktail on arrival
Arrange light bites: charcuterie, tropical fruit boards, finger foods
Set up a wireless Bluetooth sound system or hire a DJ for ambient background music
Prepare name tags or wristbands so guests can mingle with context
Brief hotel on setup: lighting, table arrangement, branded signage at entrance
Ensure Baldwin arrives last — 'grand entrance' moment to set the tone
Have Guest Services Lead manage the WhatsApp group with real-time location of mixer
Set up a guest book / Polaroid camera station for instant memories
Photographer in place 30 min before guests arrive — captures candid arrivals
✨ CREATIVE IDEAS
🍹 The 'Makena Mule' Signature Cocktail
Create a custom cocktail named after the brand. Recipe card on each table. Guests post it. Marketing.
🎙️ Live Percussionist
A local bongo or steel drum player alongside the playlist for the first hour. Sets an elevated, tropical vibe.
📓 Trip Intentions Wall
A large card or blackboard where guests write one word or intention for the trip. Photographed and shared.
🏆 'Who Are You?' Ice Breaker Game
Hosted by Guest Services Lead. Fun group game that breaks the ice without feeling forced. Prizes for winners.
🌅 Sunset Group Photo
At golden hour, photographer positions the whole group for THE group shot of the trip. Posted immediately.
💡 Glow-Up Hour
As the sun goes down, distribute glow sticks, LED bracelets and UV accessories. The energy shifts from day to night.
🎤 Welcome Speech by Baldwin
Short, personal, grateful. Sets the emotional tone. This is the moment that makes people feel like they're part of something.

## Slide 8
DAY 2
PRIVATE CATAMARAN BOAT PARTY
Delegate: Activities Coordinator + Events Lead | Vibe: Peak energy, open ocean, all day | Time: 9AM – 6PM
📋 ACTION ITEMS
Confirm catamaran booking: capacity, hours, open bar spec, crew count
Book a DJ experienced in Afrobeats / Amapiano — provide genre brief
Confirm departure marina location and arrange hotel-to-marina transport
Arrange snorkeling gear for all guests + underwater photographer
Confirm lunch menu on board — dietary requirements collected from guests in advance
Brief captain on planned stops: snorkeling reef, sandbar, open ocean cruise
Ensure safety briefing is prepared and delivered to guests before departure
Provide each guest with a waterproof bag for phones and valuables
Book an additional videographer for aerial drone footage if budget allows
Create day-of schedule and share with guests the night before
✨ CREATIVE IDEAS
🚩 Makena Flag Flying on the Catamaran
Custom Makena flag on the mast. Every photo guests take has it. Every passing boat sees it. Content gold.
🍾 Floating Charcuterie Moment
A floating tray of fruits, snacks and drinks passed around while guests are in the water at the sandbar. Instagrammable.
🌅 Sunset Champagne Toast
At the sandbar stop as the sun sets — Baldwin gives a toast. Champagne handed to every guest. Photographer captures the clink.
🎷 Live Saxophonist for One Hour
A saxophonist joins for the first hour playing over the DJ set. Elevated, unexpected. Guests go wild.
🎨 Boat Party Dress Code: Tropical Vibes
Assign a fun dress code (bright colors, florals) — different from the All White party. Group visual identity.
📸 Content Drop That Night
Content Creator delivers a 30-second boat party reel to the WhatsApp group same evening. Guests share it.
🏆 'Best Photo from the Water' Contest
Guests submit their underwater / sandbar shot to the group. Baldwin picks the winner. Small prize.

## Slide 9
DAY 3
ISLAND DAY TRIP
Delegate: Activities Coordinator | Vibe: Explorer, relaxed, scenic | Time: 8AM – 5PM (early start to beat crowds)
📋 ACTION ITEMS
Book speedboat / private ferry to island (Saona or Catalina Island recommended)
Secure EARLY departure (8AM) — arrive before the public tours overrun the beach
Confirm private beach lunch with open bar — pre-select menu, confirm dietary needs
Brief tour guide on group energy: we want fun, not a museum tour
Arrange kayaks, paddleboards or beach volleyball for free time activities
Provide Makena branded bucket hats to every guest for the day
Confirm return speedboat timing — sunset return preferred
Have Activities Coordinator on the speedboat both ways — point of contact for group
Pack a group first aid kit and sunscreen station on the beach
Arrange hotel dinner reservation for the evening — guests will be tired but hungry
✨ CREATIVE IDEAS
🎵 Local Musician on the Beach
Hire a Dominican musician (guitar or merengue) to perform during beach lunch. Authentically local. Unexpected.
📸 'Best Shot of the Day' Photo Contest
Guests submit their best island photo by 8PM. Content Creator judges. Winner gets a Makena prize pack.
🍹 Custom Island Cocktail
Work with the beach bar to create a cocktail named after the group. 'The Makena Special' — on the menu for the day.
🏐 Beach Olympics
Organize quick team games: volleyball, sandcastle contest, relay race. Teams named after Makena event nights.
🐠 Marine Life Guide
Print or post a QR code linking to a fun 'what you might see snorkeling' card. Educational & engaging.
🌺 Cultural Moment
Brief the guide to share 3 surprising facts about the Dominican Republic during the boat ride. Guests love a story.
🎥 Drone Shot at Natural Pools
If Activities Coordinator arranges drone access, the natural pools aerial shot will be THE content piece of the trip.

## Slide 10
DAY 4
ADVENTURE DAY + ALL WHITE MAKENA NIGHT PARTY
Delegate: Activities Coordinator (AM) + Events Lead (PM/Night) | The biggest night of the trip.
📋 ACTION ITEMS
Book adventure activity (dune buggies preferred — most photogenic)
Arrange transport to adventure site (7:30AM departure from hotel)
Communicate adventure dress code: old clothes you don't mind getting dirty
Confirm safety waivers distributed and signed the night before
Arrange group matching Makena jerseys/shirts for adventure day (worn over swimwear)
Book private dinner venue for 7PM — atmosphere, candles, curated menu
Send ALL WHITE reminder to every guest on WhatsApp the morning of
Brief Events Lead on party timeline: doors, DJ set, peak, close
Arrange All White entrance setup: arch, step-and-repeat, velvet rope
Confirm entry wristbands printed and distributed by Hotel Liaison at dinner
Book professional photographer + second shooter for party
Arrange sparklers and light-up accessories for midnight moment
✨ CREATIVE IDEAS
🏆 Adventure Day Race Challenge
Split into teams for the buggy race. Winning team gets bragging rights trophy (a mini golden buggy or printed certificate).
🍽️ Private Dinner: Makena Menu Card
Printed, branded menu card at each place setting. Multilingual. Live acoustic performer during dinner.
🏛️ All White Entrance Experience
Red carpet energy: step-and-repeat with Makena logo, velvet rope, bouncer, photographer at the door. Feel like a celebrity.
💡 UV Light Activation
Install UV lights at the party — all-white outfits GLOW. Hand out UV body paint pens at the entrance.
🥂 Makena Awards Ceremony
'Best Dressed All White,' 'Most Vibes,' 'MVP of the Trip' — Baldwin announces mid-party. Custom mini trophies.
🎆 Sparkler Grand Finale
At 1AM: everyone gets a sparkler. DJ drops the hardest song of the night. Photographer captures the wall of light.
🛍️ White Outfit Shop Referral
In the WhatsApp group 2 days before: a curated list of nearby shops for guests who forgot their white outfit.

## Slide 11
DAY 5
FAREWELL BREAKFAST & DEPARTURE
Delegate: Guest Services Lead + Airport Lead | Leave them wanting to book the next trip before they even land home.
📋 ACTION ITEMS
Communicate checkout times to all guests the night before (via WhatsApp)
Arrange staggered departure transfers to PUJ airport — no guest left scrambling
Reserve a private group breakfast area at the resort (7AM – 10AM)
Arrange Content Creator to compile trip highlight reel overnight (from Day 1–4 footage)
Set up a screen or TV at breakfast to play the highlight reel on loop
Prepare farewell gift for each guest (in room or handed at breakfast)
Collect and review guest feedback forms — digital link shared in WhatsApp
Final group photo in Makena gear before first departure
Settle all outstanding hotel charges before guests check out
Personally thank each delegate — recognition matters
Share post-trip social post from Makena official account same day
Send 'Thank You + Next Trip Teaser' email to all guests within 48 hours
✨ CREATIVE IDEAS
🎬 Trip Highlight Reel at Breakfast
A 60–90 second video of every day plays on a screen. Guests see themselves. Emotional moment. Everyone shares it.
📦 Farewell Gift in the Room
Guests wake up to a final Makena gift on the bed: a photo print from the trip, branded keychain, and a card that says 'See you at the next one.'
✍️ Guest Book Signing
A Makena trip journal passed around at breakfast — every guest signs a page. Baldwin keeps it as a brand artifact.
🏅 'Makena Alumni' WhatsApp Group
Create a new group at breakfast: 'Makena Punta Cana Alumni.' Keeps the community alive. Seeds the next trip's audience.
📢 Next Trip Teaser Announcement
Baldwin announces the NEXT Makena group trip at breakfast. Creates immediate FOMO and early interest.
✈️ In-Airport Surprise
Airport Lead hands each guest a small sealed envelope to open on the plane: a discount code or priority access for the next trip.
📱 Real-Time Social Takeover
Content Creator posts the reel to @makena_entertainment during breakfast. Tag the guests. The algorithm loves it.

## Slide 12
📣 MARKETING — SELLING THE TRIP ONLINE
How to fill every spot before the trip and create a waitlist for the next one.
🌐 Website (makenaevents.com/trips)
Dedicated Punta Cana trip landing page with full itinerary
Interest form live NOW — collect leads immediately
Countdown timer to booking deadline
FAQ section addressing price, flights, roommate matching
Testimonials section (use quotes from DC event attendees)
📱 Instagram Strategy
Launch a 'Punta Cana Trip' Story Highlight — keep it updated
Post a teaser reel: tropical footage + Makena music
Weekly countdown posts ('X weeks until we're in DR')
DM all previous event attendees personally — warm leads convert
Collaborate with Afrobeats/Amapiano influencers for reach
💬 WhatsApp & Community
Create a 'Punta Cana Interest List' WhatsApp broadcast
Send regular voice notes from Baldwin — personal touch drives sign-ups
Leverage DC event attendee list — they know Makena already
Offer a referral incentive: bring 2 friends, get $50 off
Weekly updates to keep the community warm
💰 Pricing & Packages
Create 2–3 tiers: Standard Room, Deluxe, VIP Suite
Offer an Early Bird rate — creates urgency and locks in cash early
Payment plan option: deposit + 2 installments
All-inclusive price — guests love knowing the total upfront
Clear 'What's Included' vs 'Not Included' breakdown

## Slide 13
💰 REVENUE MODEL & TRIP ECONOMICS
Know your numbers. Run this like a business.
These are illustrative figures — refine with your actual vendor quotes.
COST CATEGORY
EST. COST PER PERSON
NOTES
4-Night All-Inclusive Resort
$350 – $600
Negotiate group rate — target 20–30 guests
Private Catamaran (Boat Party)
$80 – $120
Split across group — private charter
Island Day Trip (Saona)
$60 – $90
Private vs. shared — go private
Adventure Day (Dune Buggies)
$70 – $100
Per person incl. transfer
Private Group Dinner
$40 – $70
Set menu + drinks per head
All White Night Party (Venue + DJ)
$50 – $80
Per person share of venue cost
Airport Transfers (Round Trip)
$30 – $50
Group van — split cost
Welcome Gift Bag (Makena Branded)
$40 – $60
Tote, towel, wristband, snacks, etc.
Content Creator / Photographer
$15 – $25
Split across group
Ground Coordinator
$10 – $20
Local hire for the week
TOTAL COST PER PERSON
$745 – $1,215
Target retail: $1,500 – $2,000+
📈 POTENTIAL MARGIN: At 25 guests paying $1,800 each = $45,000 revenue. Estimated costs at $1,100/head = $27,500. Gross margin: ~$17,500.

## Slide 14
📋 DAILY MANAGER CHECK-IN PROTOCOL
You run the team, not the tasks. These daily rituals keep you in control without doing the work yourself.
🌅 7:00 AM — Morning Standup (15 min)
Every morning: quick voice/video call with all delegates. Each person gives: • What they have confirmed for today • Any blockers or issues • What they need from you You listen, make one or two decisions, and let them execute. Keep it under 15 minutes.
📱 Throughout the Day — Delegate Pings
Each delegate sends you a simple status update at the start of each activity: 'Catamaran departed. 24 guests on board. Open bar running. DJ is great.' You reply with a thumbs up or a redirect. You are never surprised by what's happening.
🌙 9:00 PM — Evening Review (10 min)
End-of-day quick chat with Ground Coordinator: • What went well today (celebrate it) • What needs fixing for tomorrow • Confirm next day's schedule You update the group WhatsApp with a short 'Day X wrap' message to guests.
🚨 Issue Escalation Protocol
Delegates handle Level 1 (minor issues) independently. Delegate escalates Level 2 (guest complaints, vendor fail) to you via a direct call. You + Ground Coordinator handle Level 3 (medical, safety, cancellations) together immediately. No drama. Calm, decisive, fast.
📊 Budget Check (Daily)
Ground Coordinator or you reviews the daily spend against budget. Any unplanned spend over $200 requires your approval. All receipts collected daily — no chasing at the end of the trip.
🎯 Guest Pulse Check
Guest Services Lead reports guest sentiment daily: • Any concerns raised in WhatsApp? • Anyone unhappy with their room? • Any special requests for tomorrow? Proactive issue resolution = zero public complaints.

## Slide 15
WHAT HAPPENS NEXT
Your immediate action items to get this trip off the ground.
01
Launch the Punta Cana interest form on makenaevents.com/trips — NOW.
02
Post a teaser on @makena_entertainment Instagram this week.
03
DM every AfroPlusFest DC attendee personally about the trip.
04
Get 3 hotel quotes from Punta Cana all-inclusive resorts — pick one by end of month.
05
Identify and reach out to a local Punta Cana Ground Coordinator.
06
Set a booking open date and build a countdown strategy around it.
07
Design the Makena gift bag — place order 8 weeks before trip date.
08
Refine this plan with your team and assign every delegate role.
One Life. Good Vibe. Party Hard.